## Sheet1
GROUP - C
Members | GitHub
AMAN NAIN | https://github.com/amannain122
BIKKY SINGH | https://github.com/bikkysr
GAURAV SINGH | https://github.com/gaurav809
JANKIBA ZALA | https://github.com/Janki-31
PRAKASH PUN | https://github.com/prakash-pun
RUTUL PRAJAPATI | https://github.com/rutul7802
SWETHA TANIKONDA | https://github.com/Swethaloyalist
TIRTH PATEL | https://github.com/tirth-patel01
Members | Week 1-3 | Week - 4 | Week-5 | Week - 6 | Week - 7 | Week - 9 | Week - 10 | Week - 11 | Week - 12 | Week - 13
AMAN NAIN | DOCUMENTATION AND GIT CONTROLS | DATA CLEANING - weight & bp_lo column ¦DOCUMENTATION | DATA Exploration - chol, diabetes and gluco column ¦VERSION CONTROL | MULTI COLLINEARITY - Standard Scaled Data ¦ FEATURE EXTRACTION | PREAPARED TEST DATA - SCALING/OHE/CLEANING | CODE CLEANING ¦ RANDOM FOREST | XGBOOST AND LIGHTGBM AND CLASSES | MODEL TUNING - DATA DUPLICATION, GRIDSEARCHCV | RANDOM SEARCH AND LIME FOR XGBOOST, WORKED ON RESOLVING OVERFITTING | MODULARIZATION AND CODE REFACTORING, SET UP VISUALIZATION FILE
BIKKY SINGH | SCOPE OF PROJECT | DATA CLEANING - smoke column ¦ SLIDES ¦ PRESENTATION | DATA Exploration - Weight column | EDA - Univariate Analysis | FEATURE ENGINEERING - USIG STANDARD SCALED DATA | RANDOM FOREST | RANDOM FOREST | XGBOOST PARAMETER TUNING | PERFORMED LIME FOR LOGISTIC REGRESSION | DUMPED MODELS USING JOBLIB
GAURAV SINGH | DATA CLEANING | DATA CLEANING - cholesterol & glucose column | DATA Exploration - height column | EDA - Univariate Analysis | FEATURE ENGINEERING | LOGISTIC REGRESSION | NAÏVE BAYES AND LINEAR SVM | SLIDES AND PPT | PREPARED DASHBOARD USING STREAMLIT, TARGET VALUES VISUALIZATION STILL IN PROCESS | DASHBOARD USING STREAMLIT
JANKIBA ZALA | DATA CLEANING | DATA CLEANING - bp_high & gender column | DATA Exploration - bp_lo column ¦ VERSION CONTROL | EDA - Bivariate Analysis - Scaled Data ¦ VERSION CONTROL | MODULARIZATION | RANDOM FOREST | KNN | LOGISTIC REGRESSION PARAMETER TUNING | PERFORMED RANDOM SEARCH ON LOGISTIC REGRESSION | DASHBOARD USING LOOKER
PRAKASH PUN | DATA CLEANING | DATA CLEANING - age column ¦ PRESENTATION | DATA Exploration - Smoke column | SCALING - STANDARD SCALING | SETTING UP MAIN.PY ¦ MODULARIZATION | CODE CLEANING ¦ SVM | GBM AND XGBOOST AND CLASSES | GBM AND XGBOOST AND CLASSES | LIME AND RESEARCH ON STREAMLIT FOR VISUALIZATION AND DASHBOARD | DASHBOARD USING STREAMLIT, MODEL DUMPING
RUTUL PRAJAPATI | DATA COLLECTION FOR BACKUP PROJECT | DATA CLEANING - alco column ¦ VERSION CONTROL | DATA Exploration - age column ¦ TEST/TRAIN DATA SPLIT | DATA PREP - SCALING - minMAX SCALING | SLIDES - PRESENTATION | SVM | SVM | GBM PARAMETER TUNING | PERFORMED LIME FOR GBM, ERRORS YET TO BE RESOLVED | DASHBOARD USING LOOKER
SWETHA TANIKONDA | FEATURE KNOWLEDGE | DATA CLEANING - physical activity column ¦ SLIDES | DATA Exploration - bp_high column | SCALING - Scaling without Binary columns | MODULARIZATION | LOGISTIC REGRESSION | DECISION TREES AND KNN | SLIDES AND PPT | FEATURE IMPORTANT ANALYSIS | MODULARIZATION AND REFACTORED MODEL TUNERS
TIRTH PATEL | GIT CONTROLS | DATA CLEANING - bp_lo column | DATA Exploration - physical activity column ¦ weight column Documentation | MULTI COLLINEARITY | SLIDES - PRESENTATION | SVM | SVM | CHANGING IN PARAMETERS TO GET ACCURATE RESULT | PERORMED LIME FOR LOGISTIC REGRESSION, ERRORS YET TO BE RESOLVED | DASHBOARD USING LOOKER