## Sheet1
GROUP - C
Members | GitHub
AMAN NAIN | https://github.com/amannain122
BIKKY SINGH | https://github.com/bikkysr
GAURAV SINGH | https://github.com/gaurav809
JANKIBA ZALA | https://github.com/Janki-31
PRAKASH PUN | https://github.com/prakash-pun
RUTUL PRAJAPATI | https://github.com/rutul7802
SWETHA TANIKONDA | https://github.com/Swethaloyalist
TIRTH PATEL | https://github.com/tirth-patel01
Members | Week 1-3 | Week - 4 | Week-5 | Week - 6 | Week - 7 | Week - 9 | Week - 10 | Week - 11
AMAN NAIN | DOCUMENTATION AND GIT CONTROLS | DATA CLEANING - weight & bp_lo column ¦DOCUMENTATION | DATA Exploration - chol, diabetes and gluco column ¦VERSION CONTROL | MULTI COLLINEARITY - Standard Scaled Data ¦ FEATURE EXTRACTION | PREAPARED TEST DATA - SCALING/OHE/CLEANING | CODE CLEANING ¦ RANDOM FOREST | XGBOOST AND LIGHTGBM AND CLASSES | MODEL TUNING - DATA DUPLICATION, GRIDSEARCHCV
JANKIBA ZALA | DATA CLEANING | DATA CLEANING - bp_high & gender column | DATA Exploration - bp_lo column ¦ VERSION CONTROL | EDA - Bivariate Analysis - Scaled Data ¦ VERSION CONTROL | MODULARIZATION | RANDOM FOREST | KNN | LOGISTIC REGRESSION PARAMETER TUNING
GAURAV SINGH | DATA CLEANING | DATA CLEANING - cholesterol & glucose column | DATA Exploration - height column | EDA - Univariate Analysis | FEATURE ENGINEERING | LOGISTIC REGRESSION | NAÏVE BAYES AND LINEAR SVM | SLIDES AND PPT
TIRTH PATEL | GIT CONTROLS | DATA CLEANING - bp_lo column | DATA Exploration - physical activity column ¦ weight column Documentation | MULTI COLLINEARITY | SLIDES - PRESENTATION | SVM | SVM | CHANGING IN PARAMETERS TO GET ACCURATE RESULT
PRAKASH PUN | DATA CLEANING | DATA CLEANING - age column ¦ PRESENTATION | DATA Exploration - Smoke column | SCALING - STANDARD SCALING | SETTING UP MAIN.PY ¦ MODULARIZATION | CODE CLEANING ¦ SVM | GBM AND XGBOOST AND CLASSES | GBM AND XGBOOST AND CLASSES
RUTUL PRAJAPATI | DATA COLLECTION FOR BACKUP PROJECT | DATA CLEANING - alco column ¦ VERSION CONTROL | DATA Exploration - age column ¦ TEST/TRAIN DATA SPLIT | DATA PREP - SCALING - minMAX SCALING | SLIDES - PRESENTATION | SVM | SVM | GBM PARAMETER TUNING
SWETHA TANIKONDA | FEATURE KNOWLEDGE | DATA CLEANING - physical activity column ¦ SLIDES | DATA Exploration - bp_high column | SCALING - Scaling without Binary columns | MODULARIZATION | LOGISTIC REGRESSION | DECISION TREES AND KNN | SLIDES AND PPT
BIKKY SINGH | SCOPE OF PROJECT | DATA CLEANING - smoke column ¦ SLIDES ¦ PRESENTATION | DATA Exploration - Weight column | EDA - Univariate Analysis | FEATURE ENGINEERING - USIG STANDARD SCALED DATA | RANDOM FOREST | RANDOM FOREST | XGBOOST PARAMETER TUNING